## Slide 1: TIBC Budget Formulation Improvement Project
Final Recommendations and Implementation Update as of November 16, 2018
The TIBC took action on these recommendations at the July 2018 Meeting.

## Slide 2: Budget Workgroup Recommendations
Two-Way Vertical Communication
Formulation Methodology & Tribal Workload
Buy-in & Participation
TIBC Protocol & Management
Comprehensiveness of Budget Exercise
Impact of TIBC’s recommendations
PROCESS OPTION 1: Make TIBC Ranking Process bi-annual.
PROCESS OPTION 2: STAC with TIBC as a Subcommittee
Recommendations were all endorsed.
INCREASE/DECREASE METHODOLOGY: Referred to the Budget Subcommittee

## Slide 3: 1. Two-Way Communication: Recommendations
Federal
Create a communications protocol. In progress.
Update the Budget Guidance. Done.
Creation of a website. In progress. TIBC Tribal
Develop protocol on TIBC reps responsibility to communicate to tribes in their region. In progress.
Designate a TIBC POC in charge of confirming that outreach and
communication is taking place in compliance with the new protocol. In progress.

## Slide 4: 2. Formulation Methodology & Tribal Workload: Recommendations
Survey
Recommendation: continue to utilize the preferred program ranking tool process with the updates recommended in this section. The 2020 priority survey yielded largely positive feedback from the tribes.

## Slide 5: 3. Buy-in & Participation: Recommendations
Valuing the Process
Need to ensure that all TIBC members value the formulation process by updating TIBC protocol. This is on agenda next.
Reduce the number of meetings and streamline and reformat the remaining meetings. Done.

## Slide 6: 3. Buy-in & Participation: Recommendations
Ensure that the Subcommittees are reporting out only when they have a decision point.
Need to ensure that the goals and purposes of the non-standing
subcommittees are clear.
Ensure that marketing of TIBC to tribes is more consistent.
Ensure that the tribes are involved in selection of their TIBC rep and feel a part of the process.
Included in protocol changes.
Ensure that federal partners make a commitment. Letter being drafted.
Federal partners from each of the budget programs (especially the priority areas) should use TIBC as an opportunity to report-out on the programs, budget, etc. Added to agendas.

## Slide 7: 4. TIBC Protocol & Management: Recommendations
New Member Orientation
Recommend development of an orientation program for new TIBC members. In
person orientation done this week. Follow up webinar recording in process.
Meeting Facilitation, Tracking, and Follow-Up
TIBC should conduct a process to identify coordination gaps that exist between the roles of TIBC, BIA and NCAI. In progress.
Ensure that the role of TIBC is articulated. In Guidance and Orientation.
Ensure that the budget process is clearly laid out for reps. In Guidance and Orientation.

## Slide 8: 5. Comprehensiveness of Budget Exercise: Recommendations
Create a more comprehensive process by expanding the scope of the budget consultation at the DOI and all-of-government levels. DOJ involvement. Requested at OMB meeting.
The BIE survey needs to be well-coordinated with TIBC and the BIA survey in terms of target audience, timing, and workload. Addressed in guidance and ranking tool.

## Slide 9: 6. Impact of TIBC’s Recommendations: Recommendations
Develop an outreach and briefing strategy for federal officials. In process.
Clarify to tribes in the budget formulation guidance where their information will end up. In Guidance and orientation.
NCAI should facilitate Hill engagement for TIBC tribal co- chairs. In process for FY 2020 spring cycle.

## Slide 10: 7. PROCESS CHANGE OPTION 1
Move the annual TIBC budget formulation process to a bi-annual process.
Adopted pending second approval at the April 2019 TIBC meeting.

## Slide 11: 8. PROCESS CHANGE OPTION 2
Elevate, Refocus and Narrow TIBC’s Mission. Create a STAC with TIBC as a Subcommittee
Approved on a conceptual basis with details to be worked out and approved at a later TIBC meeting.

## Slide 12: Current
TIBC
BUDGET
ROADS
PUBLIC
SAFETY
Edu.
DATA
SECRETARY’S TRIBAL ADVISORY COUNCIL
EDUCATION
PUBLIC SAFETY
ROADS
TIBC
BUDGET SUBCOMMITTEE
TIBC
DATA MANAGEMENT
New

## Slide 13: 9. INCREASE SCENARIO
The Budget Subcommittee has reviewed a new approach to distributing an increase in future budget increase exercises.
The formula would distribute increases among the top-ranked programs in a manner that is weighted by:
  1) Priority level
  2) Size of program
Decision: the Budget Subcommittee will evaluate different options for specific allocation of increases to TPA, CSC, and TPA-like programs.

## Slide 14: 9. DECREASE SCENARIO
TIBC should conduct a process to determine whether or not TIBC will engage in a decrease scenario exercise. Depending on the decision of the TIBC reps, create a formula for handling the decrease scenario.
Decision: TIBC will not officially refuse to engage in the decrease scenario exercise but reserves their prerogative to make this decision on an annual basis.

## Slide 15
Date | Activity
OCT 19, 2018 | The Office of Budget and Performance Management (OBPM) releases budget formulation guidance and ranking tool to the regions and tribes via Kick off webinar.
OCT 2018 – JAN 2019 | Tribes receive ranking tool and formulation guidance. Regions hold their tribal budget formulation meetings/work sessions for FY 2021.
JAN 10, 2019 | All tribal ranking tool submissions must be in to regional offices.
FEB 10, 2019 | Regions submit tribal ranking roll up and federal regional request templates.
FEB 2019 | Regional submissions shared with Central Office (CO) program staff for use in formulating their budgets. OBPM prepares National Roll up from regional submissions.

## Slide 16
Date | Activity
MAR 15, 2019 | CO program submissions are sent to OBPM.
MAR 18-29, 2019 | CO Program Briefings are conducted by OBPM
APRIL 9-11, 2019 | Results of the Regional and National Rollups presented to the full TIBC Body by OBPM at April Session. The TIBC body deliberates at the April Session and determines budget strategy for FY 2021.
APRIL 12, 2019 | Budget Subcommittee work session to develop tribal budget submission.
APRIL 16, 2019 | Subcommittee presents proposed budget and draft testimony to full TIBC Committee for approval via webinar.
APRIL 18, 2019 | Tribal Presentation of approved tribal budget and testimony to the Assistant Secretary – Indian Affairs.

## Slide 17
Date | Activity
APRIL 22, 2019 | OBPM prepares Budget Deliberation Books to include all tribal, regional, and CO submissions.
APRIL 24- MAY 8, 2019 | IA Budget deliberations with Senior Management.
MAY 2019 | Departmental submission for FY 2021.
MAY/JUNE 2019 | Indian Affairs will assist in the scheduling of a meeting among the co- chairs of the TIBC, representatives, and the Director of the Office of Management and Budget (OMB).
JULY 2019 | TIBC Budget Meeting, Alaska.
SEPT 2019 | OMB Submission for FY 2021.
OCT 2019 | FY 2022 Budget Formulation begins.
NOV 2019 | OMB Passback on FY 2021 Budget.
FEB 2020 | FY 2021 Greenbook goes to print.